## Summary
Project Name | Web Test Automation
Reference Document | http://123.200.20.20:5302/
Created By | Abu Md Salahuddin
Creation Date | DD-MM-YYYY
Approval Date | DD-MM-YYYY
Test Case Summary Report
TOTAL TEST CASE | PASSED | FAILED | NOT TESTED
15 | 12 | 3 | 0
Bug List Summary Report
TOTAL BUGS | TO DO | IN PROGRESS | DONE | FAILED
3 | 3 | 0 | 0 | 3

## TestCase
[9 empty] | FAILED | 3
15 | [8 empty] | PASSED | 12
S.No | Test Case ID | Req. ID | Bug ID | Screen Name | Test Description | Actor | Steps to Follow | Expected Result | Actual Result | Cycle 1
1 | TC_01 | Web application |  | Open the web aplication | Dashboard information verify | Anonyms | Open the URL: http://123.200.20.20:5302/ in web browser | Dashboard information will be displayed with circular list and info contains Circular No., Publish Date, Start Date, End Date, Status, and Action | As Expected | PASSED
2 | TC_02 | Web application | Bug_002 | Circular List | Circular Search | Anonyms | Input Circular number in the search box then press ENTER | The designated Circular number will display successfully | Search function not working | FAILED
3 | TC_03 | Web application | Bug_001 | Circular List | Circular details | Anonyms | Click on the designated Circular number | The selected Circular number detail information will display successfully | The selected Circular number detail information displays in another tab window | FAILED
4 | TC_04 | Web application |  | Circular List | Circular Download | Anonyms | Click on the Circular download icon | The selected Circular number detail information download successfully | As Expected | PASSED
5 | TC_05 | Web application | Bug_003 | Circular List | Circular sorting | Anonyms | Click on each of the ‘Circular No.’, ‘Publish Date’, ‘Start Date’, ‘End Date’, ‘Status’, ‘Action’ sorting icon | All of the sorting should works properly | Only ‘Circular No.’ sorting works properly | FAILED
6 | TC_06 | Web application |  | Post vacancy | Selected Circular more detail information | Anonyms | Click on the action icon | Selected Circular more detail information will display successfully | As Expected | PASSED
7 | TC_07 | Web application |  | Apply Now | Apply now | Anonyms | Click on the apply now button | Login to apply screen will display with options | As Expected | PASSED
8 | TC_08 | Web application |  | Login to apply | Continue without Login | Anonyms | Click on the Continue without Login button | Job Application Basic Information entry screen will display | As Expected | PASSED
9 | TC_09 | Web application |  | Basic Information | Verify NID | Anonyms | Enter the National ID, National ID Attachment, Date of Birth then click on Verify NID button | If NID information matched then detail personal information will display successfully | As Expected | PASSED
10 | TC_10 | Web application |  | Basic Information | Personal Info enter | Anonyms | After keyed the required personal information then click on the Next button | If all the personal information input correctly then successfully moved to the Address screen | As Expected | PASSED
11 | TC_11 | Web application |  | Address | Address Info enter | Anonyms | Enter all the required Address information then click on the Next button | If all the address information input correctly then successfully moved to the Education screen | As Expected | PASSED
12 | TC_12 | Web application |  | Education | Education Info enter | Anonyms | Enter all the required Education information then click on the Next button | If all the Education information input correctly then successfully moved to the Job Experience screen | As Expected | PASSED
13 | TC_13 | Web application |  | Job Experience | Job Experience Info enter | Anonyms | Enter all the required Job Experience information then click on the Next button | If all the Job Experience information input correctly then successfully moved to the Complete screen | As Expected | PASSED
14 | TC_14 | Web application |  | Certificate | Certificate Info enter | Anonyms | Enter all the required Certificate information then click on the Next button | If all the Job Experience information input correctly then successfully moved to the Complete screen | As Expected | PASSED
15 | TC_15 | Web application |  | Complete | Declaration make | Anonyms | Click on the Declaration checkbox then click on the complete button then click on Yes for final confirmation | Job application will be successfully send and confirmation info will be displayed in the screen | As Expected | PASSED

## Bug_List
[7 empty] | To Do | 3 | Failed | 3
TOTAL BUGS | 3 | [5 empty] | In Progress | 0 | Done | 0
DATE | Bug ID | Req. ID | Bug Description | Steps to reproduce | Test Data | Screenshot | Remarks | Dev Status | Script | Cycle -1 QC status
| Bug_001 | Web Test | When select and click on a particular circular that time a new window tab open to view the details | 1. Open the URL: http://123.200.20.20:5302/ in web browser 2. Click on the a particular Circular number |  |  | OPEN BUG | TO DO |  | FAILED
| Bug_002 | Web Test | Search function not working | 1. Open the URL: http://123.200.20.20:5302/ in web browser 2. Input Circular number in the search box then press ENTER |  |  | OPEN BUG | TO DO |  | FAILED
| Bug_003 | Web Test | ‘Publish Date’, ‘Start Date’, ‘End Date’, options sorting not works | 1. Open the URL: http://123.200.20.20:5302/ in web browser 2. Click on each of the ‘Circular No.’, ‘Publish Date’, ‘Start Date’, ‘End Date’, ‘Status’, ‘Action’ sorting icon |  |  | OPEN BUG | TO DO |  | FAILED